## backlog
|  |  | As <WHO>, I want/need to <WHAT> so that <WHY>. |  |  |  | As <WHO>, I want/need to <WHAT> so that <WHY>.
WHO for the Role
NAME OF THE SOFTWARE: CheckMyZip |  |  | WHAT for Capability, Task, Hard-goal, and Soft-goal |  |  |  | WHO for the Role
|  |  | WHY for Task, Hard-goal, and Soft-goal |  |  |  | WHAT for Capability, Task, Hard-goal, and Soft-goal
Product owner: GOLDEN BAR | [6 empty] | WHY for Task, Hard-goal, and Soft-goal
Date of creation: 10/8/2019
Nielsen my best segments
ID | Name | Creation Date | Description | Size | Priority | Dependencies | Notes | Sprint | Responsibility
US1 | Finding database | 2019-08-10 | Finding database with the information app wants to provid user and list items. | Large | High |  | This will first need a survey to see what people might be interested in, then find out if those informations are available
US2 | Fetching data | 2019-08-10 | Fetch data from database and stroe in local database | large | High | backend | Determine if data should be stored or accessed form third party database per query
US3 | Analyze data | 2019-08-10 | Analyze data to summizing the data for each city | Large | High | US2 | Determine how to present data in picture, tabular form, graphs, charts etc
US4 | Login User | 10/14/2019 | Building a database which is storing users' account number. password, and other information. On one page, we need to provide the area which allows user to sign up a new account stored in user database, and to login the app.
US5 | Zip code | 10/14/2019 | Once user logged in, there is one page allowing users to enter zip code and the app return the information based on the zip code
US6 | Weather information | 10/14/2019 | By the each zip code, there is
US7 | Build maping page | 2019-08-10 | User should be able to see a map when they put in a more generic (City name, state, county name) information over specific zip code. | Large | Medium |  | This may be achieved: Build a map page which can link to google map. Get the GPS information from google maps.
US8 | Pop Notification about area | 2019-08-10 | Based on the gps information provided by google map. The app presents a pop up notification about recent news, crime rate, traffic and so on, about the area. | Medium | Medium | US4 | Using location technology
US9 | Display the weather information | 2019-08-10 | Based on the area location, the app present the average weather condition and temperature. | Small | Low | US2
US10 | Build fliter and checklist | 2019-08-10 | Build a fliter with check item, so user can select the information they want to know and narrow it down to their best interest | Large | Medium
US11 | Build a database store user information | 2019-08-10 | Build a database storing user account number, passwords, and other information. | Medium | High | US2
US12 | First page | 2019-08-10 | On the first page, there is a search bar that users can type in zip code or city name. After user click search buttom, next page will present the information of the city. | Medium | High
US13 | Handicap support | 2019-08-10 | If user is handicapped, location technology should be ale to tell them if they are side walks around, elevator in/out facilities and subway. | Large | Low | US9 | Will provide handicap support and make accesibility easier. It will also suggest areas with organizations that support specific conditions.
US14 | Find my commuinity | 2019-08-10 | Based on user info, including age, race, country of origin, stated interests, religion, and gender/sexuality, app will suggests unions, groups, organizations that provide support, and places of worship. | Medium | Medium | US9 | App will help user find people with common interest.
US15 | Area background check | 2019-08-10 | For user wanting to move, present relevant informations about areas they are interested in, including crime rate, school standing, average rent, level of education of residents, different demographics of the residents, Police ratings, health care facility ratings, access to transportation and number of commuters, and hospitals that could handle pre-existing conditions. | Large | High | US9 | Go into the database to get all information known about a specific zipcode, or extract data from bearue of statistics, and population census etc.
US16 | Comparing zip codes | 2019-08-10 | User check criterias and put in two zip codes. Results for both areas will be shown side by side. For example, user can compare school standings, and both results will be gathered and show to user. | Large | Medium | US9 | Given the criteria marked by user, app will provide the info on a tabular form comparing both areas.
US17 | Breaking news | 2019-08-10 | User will get pop up notifications of breaking news around the zipcode they provided as "home" | Large |  | US9 | This source for news using user zipcode, and presents it as a notification
US18 | Local Political representatives and their contact information | 2019-08-10 | User will be able to access a page with information of their political representatives | Large | Low | US3 | The information they can find will include name, picture if possible, office held, and contact information.
US19 | Home page | 2019-08-10 | Home page should be intuitive. Icons should be so easy that non native speakers can navigate app. | Medium | High | US13 | Home page will include, profile, search bar, and notification.
US20 | Give user option to find suitable neighborhood that might fit need including amenities, income, level of education and ethnicity |  | The tags should make sense and should be able to use keywords that could match what they are looking for. |  |  |  | We might have to search what other people have done in crunching data and presenting results.
US21 | Password retriver system |  | If users forget their password, there is one page for them to receive password via email. User will get to page and fill in Email or answer security question.
US22 | Security question and answer |  | Add security questions and answers on registration process which will be used during registration
US23 | Email Validation |  | Add email validation in registration process to prevent spam. After sumbitting the registration form, user will receive email that contains a link to confirm the registration.
US24 | Database security |  | Add security rules to database and update priviledges

## Sprint 1
Sprint 1 backlog |  |  | GOLDEN BAR
ID | Name | Creation Date | Description | Size | Priority | Dependencies | Notes | Sprint | Responsibility
US1 | Account database | 10/15/2019 | Creating a database storing user information | medium | high |  |  | 1
US2 | Login User | 10/15/2019 | Building a database which is storing users' account number. password, and other information. On one page, we need to provide the area which allows user to sign up a new account stored in user database, and to login the app. | small | high | us1 |  | 1
US3 | User sign up | 10/15/2019 | Creating a page for user to sign up and storing the information to user databsae | small | high | us1
US4 | Enter zip codes | 10/15/2019 | An text box which allow user to enter zip code and return the information of the zip code | Large | high |  |  | 1
US5 | Home page | 10/15/2019 | Home page should be intuitive. Icons should be so easy that non native speakers can navigate app. | Medium | High |  | Home page will include, profile, search bar, and notification. | 1
US6 | Weather | 10/15/2019 | Using google API to provide the weather condition, include historical weather information and live weather. Historical weather condition includes average week, month, quater temparture. | Medium | medium |  |  | 1
US7 | Demographic information | 10/15/2019 | Data includes population, race, nation, and etc | Medium | medium |  |  | 1
US8 | Income | 10/15/2019 | The average income of the people living in the area | Medium | medium |  |  | 1
US9 | First page | 10/15/2019 | the first page of app | small | low |  |  | 1

## Sprint 2
Sprint 2 backlog |  |  | GOLDEN BAR
ID | Name | Creation Date | Description | Size | Priority | Dependencies | Notes | Sprint | Responsibility
US4 | Password retriver system |  | If users forget their password, there is one page for them to receive password via email. User will get to page and fill in Email or answer security question. | Medium | High |  |  | 2 |  | 1
US5 | Security question and answer |  | Add security questions and answers on registration process which will be used during registration | Small | HIgh |  |  | 2 |  | 1
US4 | Email Validation |  | Add email validation in registration process to prevent spam. After sumbitting the registration form, user will receive email that contains a link to confirm the registration. | Medium | High |  |  | 2 |  | 1
US3 | Database security |  | Add security rules to database and update priviledges | Large | HIgh |  |  | 2
US8 | Enter zip codes | 10/15/2019 | An text box which allow user to enter zip code and return the information of the zip code | Large | high |  |  | 1
US5 | Home page | 10/15/2019 | Home page should be intuitive. Icons should be so easy that non native speakers can navigate app. | Medium | High |  | Home page will include, profile, search bar, and notification. | 1
US6 | Weather | 10/15/2019 | Using google API to provide the weather condition, include historical weather information and live weather. Historical weather condition includes average week, month, quater temparture. | Medium | medium |  |  | 1
US7 | Demographic information | 10/15/2019 | Data includes population, race, nation, and etc | Medium | medium |  |  | 1
US8 | Income | 10/15/2019 | The average income of the people living in the area | Medium | medium |  |  | 1
US9 | First page | 10/15/2019 | the first page of app | small | low |  |  | 1

## Sheet3
ID | Name | Creation Date | Description | Size | Priority | Sprint | Responsibility | Reliability requirements
US5 | Security question and answer |  | Add security questions and answers on registration process which will be used during registration | Small | HIgh | 2 |  | Security question is picked from a list of question and user answer it. The data is sent to database under related to user's unique id. The answer have to match the question. For example, the answer 1 is only for question 1.
US2 | Login User | 10/15/2019 | Building a database which is storing users' account number. password, and other information. On one page, we need to provide the area which allows user to sign up a new account stored in user database, and to login the app. | small | high | 1 |  | The user login system is supported by firebase. The system will show the error message, If there are following condition: user left either or both email or password empty, user's password and account is not matched, the email is not verified, and the account is not in database. There is a default condition to prevent some unknown condition happened to crash the app.
US3 | User sign up | 10/15/2019 | Creating a page for user to sign up and storing the information to user databsae | small | high |  |  | User have to enter required information to sign up an account. If there is something missed, the system will give hints to users. The password is masked by dots, and should only contain letters, numbers and some spicial symbols. The email have to be correct format like xxx@xxx.xxx. If the information users provided anginest the rules, proper information will show up.

## Sprint 3
ID | Name | Creation Date | Description | Size | Priority | Dependencies | Notes | Sprint | Responsibility
US7 | Demographic information | 10/15/2019 | Data includes population, race, nation, and etc | Medium | medium |  |  | 1
US8 | Income | 10/15/2019 | The average income of the people living in the area | Medium | medium |  |  | 1
US1 | Finding database | 2019-08-10 | Finding database with the information app wants to provid user and list items. | Large | High |  | This will first need a survey to see what people might be interested in, then find out if those informations are available
US2 | Fetching data | 2019-08-10 | Fetch data from database and stroe in local database | large | High | backend | Determine if data should be stored or accessed form third party database per query
US3 | Analyze data | 2019-08-10 | Analyze data to summizing the data for each city | Large | High | US2 | Determine how to present data in picture, tabular form, graphs, charts etc
US5 | Home page | 10/15/2019 | Home page should be intuitive. Icons should be so easy that non native speakers can navigate app. | Medium | High |  | Home page will include, profile, search bar, and notification. | 1
US6 | Weather | 10/15/2019 | Using google API to provide the weather condition, include historical weather information and live weather. Historical weather condition includes average week, month, quater temparture. | Medium | medium |  |  | 1
| Local News |  | Give updates on news around zip code | Medium | High
| Traffic update |  | Provide traffic information | Large | High